## SDEV 1031
Course Timeline SDEV 1031 - 90 hours (Re-Enrolled)
| Start Date: | 2018-09-17 |  | Enter start and end dates for your course in MM/DD/YYYY format here
| End Date: | 2018-10-25
| Days / Week | 2 , 3
| Hours / Day | 6
| Hours / Week | 12,18
Record your actual start and end dates here to use when reporting on progress
Module | Hours | Start | End | Actual Start | Actual End
1 | 20 | 2018-09-17 | 2018-09-25 | 2018-09-17 | 2018-09-26
2 | 14 | 2018-09-25 | 2018-10-01 | 2018-09-26 | 2018-10-31
3 | 16 | 2018-10-01 | 2018-10-05 | 2018-10-31 | 2018-11-06
4 | 18 | 2018-10-05 | 2018-10-11 | 2018-11-08 | 2018-11-27
5 | 12 | 2018-10-11 | 2018-10-23 | 2018-11-27 | 2018-12-11 | <- like 1 hr in 12/11
6 | 10 | 2018-10-23 | 2018-10-25 | 2018-12-11
^THESE ARE THE ORIGINAL DATES^
Using the number of hours in a module, determine the end date of the first module | [5 empty] | EXAMPLE -- Calendar View
In this example, the students comes in 5 days a week, 3 hours a day, for 15 hours a week. | [5 empty] | Mon | Tues | Wed | Thur | Fri
The first module is 20 hours, and the student comes in 15 hrs a week, | [5 empty] | 2015-02-23 | 2015-02-24 | 2015-02-26 | 2015-02-26 | 2015-02-27
so the first week will be 15 hours of the 20-hour module, with 5 hours left. | [5 empty] | 3 hrs | 3 + 3 = 6 | 6 + 3 = 9 | 9 + 3 = 12 | 12 + 3 = 15
The first day of the next week is 3 of those 5 hours, with 2 hours left in the second day.
So the end date for module 1 is the second day of the second week. | [5 empty] | 2015-03-02 | 2015-03-03 | 2015-03-04 | 2015-03-05 | 2015-03-06 | 3/3: 2 hrs M1, 1 hr M2
Because there is an hour left in that day, the second module starts on the same day. | [5 empty] | 15 + 3 = 18 | 18 + 2 = 20 | 1 + 3 = 4 | 4 + 3 = 7 | 7 + 3 = 10
Continue calculating how long each module will take given the student's schedule. | [6 empty] | 1 hr
[6 empty] | 2015-03-09 | 2015-03-10 | 2015-03-11 | 2015-03-12 | 2015-03-13 | 3/10: 1 hr M2, 2 hr M3
[6 empty] | 10 + 3 = 13 | 13 + 1 = 14 | 2 + 3 = 5 | 5 + 3 = 8 | 8 + 3 = 11
EXAMPLE | [6 empty] | 2 hrs
Module | Hours | Start | End |  |  | 2015-03-16 | 2015-03-17 | 2015-03-18 | 2015-03-19 | 2015-03-20 | 3/17: 2 hr M3, 1 hr M4
1 | 20 | 2018-09-17 | 2015-03-03 | colors of modules |  | 11 + 3 = 14 | 14 + 2 = 16 | 1 + 3 = 4 | 4 + 3 = 7 | 7 + 3 = 10
2 | 14 | 2015-03-03 | 2015-03-10 | are reflected in the |  |  | 1 hr
3 | 16 | 2015-03-10 | 2015-03-17 | calendar view to |  | 2015-03-23 | 2015-03-24 | 2015-03-25 | 2015-03-26 | 2015-03-27 | 3/25: 2 hr M4, 1 hr M5
4 | 18 | 2015-03-17 | 2015-03-25 | the right |  | 10 + 3 = 13 | 13 + 3 = 16 | 16 + 2 = 18 | 1 + 3 = 4 | 4 + 3 = 7
5 | 12 | 2015-03-25 | 2015-03-31 |  |  |  |  | 1 hr
6 | 10 | 2015-03-31 | 2018-10-25 |  |  | 2015-03-30 | 2015-03-31 | 2015-04-01 | 2015-04-02 | 2015-04-03 | 3/31: 2 hr M5, 1 hr M6
[6 empty] | 7 + 3 = 10 | 10 + 2 = 12 | 1 + 3 = 4 | 4 + 3 = 7 | 7 + 3 = 10
1 hr
|  |  |  | Mon | Tues | Wed | Thur | Fri
|  |  |  | 2015-02-23 | 2015-02-24 | 2015-02-26 | 2015-02-26 | 2015-02-27
|  |  |  | 2015-03-02 | 2015-03-03 | 2015-03-04 | 2015-03-05 | 2015-03-06 |  | 3/3: 2 hrs M1, 1 hr M2
|  |  |  | 2015-03-09 | 2015-03-10 | 2015-03-11 | 2015-03-12 | 2015-03-13 |  | 3/10: 1 hr M2, 2 hr M3
|  |  |  | 2015-03-16 | 2015-03-17 | 2015-03-18 | 2015-03-19 | 2015-03-20 |  | 3/17: 2 hr M3, 1 hr M4
|  |  |  | 2015-03-23 | 2015-03-24 | 2015-03-25 | 2015-03-26 | 2015-03-27 |  | 3/25: 2 hr M4, 1 hr M5
|  |  |  | 2015-03-30 | 2015-03-31 | 2015-04-01 | 2015-04-02 | 2015-04-03 |  | 3/31: 2 hr M5, 1 hr M6